## Summary
Squeeze Summary
| FY Targeted | FY Forecast
|  | Non Proc | Proc | Total | Gap
Planned | 500 | 203.6667 | 0 | 203.6667 | -296.3333
Targeted | 500 | 0 | 1373.8089 | 1373.8089 | 873.8089
Planning | 500 | 112.2904 | 0 | 112.2904 | -387.7096
TOTAL | 1500 | 315.9571 | 1373.8089 | 1689.766 | 189.766
Department
R&D
Packaging
Procurement
Mktg

## STATUS TRACKER
[10 empty] | Actuals | Actuals | ESTD | ESTD | ESTD | ESTD | ESTD | ESTD | ESTD | ESTD | ESTD | ESTD
[8 empty] | MONTH → |  | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | Total
Type | Project Code | Material Code | Brand - Activity | Head | Status | DOI (Ini) | DOI (rev) | DOI (Calc) | Annualised Savings | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | Amount
Proc | TG-2324-RM01 | 4000310 | ACULYN 33 | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 3480000 | 348332.7229 | 232969.6663 | 290000 | 290000 | 290000 | 290000 | 290000 | 290000 | 290000 | 290000 | 290000 | 290000 | 3481302.3891
Proc | TG-2324-RM02 | 4000178 | CYCLOPENTASILOXANE | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 318000 | 0 | 0 | 26500 | 26500 | 26500 | 26500 | 26500 | 26500 | 26500 | 26500 | 26500 | 26500 | 265000 | Material not lifted
Proc | TG-2324-RM03 | 4000225 | N-HANCE CG-17/JAGUAR C-17/ARMOCARE G114 | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 3603000 | 202493.1769 | 129065.0273 | 300250 | 300250 | 300250 | 300250 | 300250 | 300250 | 300250 | 300250 | 300250 | 300250 | 3334058.2042
Proc | TG-2324-RM04A | 4000129 | CAPB (COCAMIDOPROPYL BETAINE 30%) | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 378228 | 12967.2372 | 162282.2895 | 31519 | 31519 | 31519 | 31519 | 31519 | 31519 | 31519 | 31519 | 31519 | 31519 | 490439.5267
Proc | TG-2324-RM04B | RCC-00952 | CAPB (COCAMIDOPROPYL BETAINE 30%) - Nikita | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 720000 | 289286.6711 | 0 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 889286.6711 | Nikita
Proc | TG-2324-RM05 | 4000223 | BELSIL CK 9819 | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 746946.6667 | 65850 | 140100 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 62245.5556 | 828405.5556
Proc | TG-2324-RM06 | 4000146 | SODIUM SULPHATE ANHYDROUS | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 35800 | 60548.9711 | 3952.9744 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 2983.3333 | 94335.2788
Proc | TG-2324-RM07 | 4000376 | PRECIPITATED SILICA POWDER | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 146200 | 20298.4948 | 0 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 12183.3333 | 142131.8282
Proc | TG-2324-RM08 | 4000097 | EDTA DI Sodium | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 425500 | 2859.289 | 27752.9958 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 35458.3333 | 385195.618
Proc | TG-2324-RM09 | 4000241 | AQUACID 600-S | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 682500 | 15984.5336 | 117175.3277 | 56875 | 56875 | 56875 | 56875 | 56875 | 56875 | 56875 | 56875 | 56875 | 56875 | 701909.8613
Proc | TG-2324-RM10 | 4000102 | RESORCINOL | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 1470015 | 465207.0103 | 511865.6838 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 122501.25 | 2202085.1941
Proc | TG-2324-RM11 | 4000373 | HYDROGEN PEROXIDE (H2O2) 50% | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 1736000 | 0 | 0 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 144666.6667 | 1446666.6667 | UKM1 already started and ASM1 is pending
Proc | TG-2324-RM12 | 4000218 | Carbopol 980/Acrypol 980/Biopol 980 | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 8174833.3333 | 0 | 501135.7441 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 681236.1111 | 7313496.8552
Proc | TG-2324-RM14A | 4000224 | CLIMBAZOLE (CRINIPAN/DANTUFF/SALIZOLE) | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-05-01 | 5880000 | 0 | 570049.7391 | 490000 | 490000 | 490000 | 490000 | 490000 | 490000 | 490000 | 490000 | 490000 | 490000 | 5470049.7391
Proc | TG-2324-RM14B | 4000224 | CLIMBAZOLE (CRINIPAN/DANTUFF/SALIZOLE) | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 3520000 | 0 | 0 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 293333.3333 | 2933333.3333
Proc | TG-2324-RM15 | 4000507 | Polyox WSR N 60K | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2400000 | 55964.7383 | 191898.5483 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 2247863.2866
Proc | TG-2324-RM16A | 4000180 | EGDS (GLYCOL DISTEARATE) / Cutina AGS | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-07-01 | 471450 | 0 | 0 | 0 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 39287.5 | 353587.5
Proc | TG-2324-RM16B | 4000180 | EGDS (GLYCOL DISTEARATE) / Cutina AGS | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 252562.5 | 40365.4243 | 81152.7441 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 21046.875 | 331986.9184
Proc | TG-2324-RM17 | 4000133 | Jaguar c13 | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-07-01 | 31500 | 0 | 0 | 0 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 23625
Proc | TG-2324-RM18 | 4000163 | sodium CMC | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-08-01 | 575400 | 0 | 0 | 0 | 0 | 47950 | 47950 | 47950 | 47950 | 47950 | 47950 | 47950 | 47950 | 383600
Proc | TG-2324-RM19 | 4000211 | Kathon CG | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 1431456 | 5297.1429 | 5559.2143 | 119288 | 119288 | 119288 | 119288 | 119288 | 119288 | 119288 | 119288 | 119288 | 119288 | 1203736.3571
Proc | TG-2324-RM20 | 4000104 | Sodium Perborate monohydrate | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 7774200 | 0 | 0 | 0 | 0 | 0 | 0 | 647850 | 647850 | 647850 | 647850 | 647850 | 647850 | 3887100
Proc | TG-2324-RM21 | 4000186 | GLYCERYL MONO STEARATE -SE | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 1910700 | 0 | 0 | 0 | 0 | 0 | 0 | 159225 | 159225 | 159225 | 159225 | 159225 | 159225 | 955350
Proc | TG-2324-RM22 | 4000270 | HEAP | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-06-01 | 472500 | 8500 | 0 | 39375 | 39375 | 39375 | 39375 | 39375 | 39375 | 39375 | 39375 | 39375 | 39375 | 402250 | Need to received Confirmation from R&D
Proc | TG-2324-RM23 | 4000227 | 2DPE HCL | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-07-01 | 4745625 | 0 | 562931.6999 | 0 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 395468.75 | 4122150.4499
Proc | TG-2324-RM24 | 4000325 | MAP | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-07-01 | 1542000 | 0 | 0 | 0 | 128500 | 128500 | 128500 | 128500 | 128500 | 128500 | 128500 | 128500 | 128500 | 1156500
Proc | TG-2324-RM25 | 4000191 | IPM | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 20000 | 0 | 21395.75 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 38062.4167
Proc | TG-2324-RM26 | 4000112 | CCTG | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 100000 | 0 | 112370.1765 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 195703.5098
Proc | TG-2324-RM27 | 4000334 | D-panthenol | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-06-01 | 587000 | 0 | 0 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 48916.6667 | 489166.6667
Proc | TG-2324-RM28 | 4000178 | CYCLOPENTASILOXANE - E | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 1114285.7143 | 0 | 0 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 92857.1429 | 928571.4286
Proc | TG-2324-RM29 | 4000139 | PQ7-40 (SALCARE SUPER 7/ MERQUAT 740) | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-09-01 | 1196667 | 0 | 0 | 0 | 0 | 0 | 99722.25 | 99722.25 | 99722.25 | 99722.25 | 99722.25 | 99722.25 | 99722.25 | 698055.75
Proc | TG-2324-RM30 | 4000160 | PLANTACRE 1200 (LAURYL GLUCOSIDE) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-06-01 | 872860 | 0 | 0 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 72738.3333 | 727383.3333
Proc | TG-2324-RM31 | 4000186 | GLYCERYL MONO STEARATE -SE (GMS -SE) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-06-01 | 447405 | 0 | 0 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 37283.75 | 372837.5
Proc | TG-2324-PM01 | 5001635/5001639/ 5002668 | Meera Bi layer bottle - 340ML - Production shifting from Baddi to Guwahati | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 2124000 | 0 | 0 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 1770000
Proc | TG-2324-PM02 | 5002665/ 5001644/ 5006732 /5001649 | Meera Bi layer bottle- 640 ml Production shifting from Baddi to Guwahati | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-08-01 | 1452000 | 0 | 0 | 0 | 0 | 121000 | 121000 | 121000 | 121000 | 121000 | 121000 | 121000 | 121000 | 968000
Proc | TG-2324-PM03 | 5001731 | Meer AD - 80 ml - Moulding / Metallization - Single Source | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-07-01 | 1500000 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1125000
Proc | TG-2324-PM04 | 5001732 | Meer AD - 180 ml - Moulding / Metallization - Single Source | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-07-01 | 2270000 | 0 | 0 | 0 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 189166.6667 | 1702500
Proc | TG-2324-PM05 | 5006068 | Meera Hari wash Powder - Cap - 120 ml - Metallization to Pigment | Sivaraj | Cancelled | 2023-04-01 | 2023-04-01 | 2023-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proc | TG-2324-PM06 |  | MCO - 25 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 304640 | 0 | 0 | 0 | 0 | 0 | 0 | 25386.6667 | 25386.6667 | 25386.6667 | 25386.6667 | 25386.6667 | 25386.6667 | 152320
Proc | TG-2324-PM07 |  | MCO - 100 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 235200 | 0 | 0 | 0 | 0 | 0 | 0 | 19600 | 19600 | 19600 | 19600 | 19600 | 19600 | 117600
Proc | TG-2324-PM08 |  | MCO - 175 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 385840 | 0 | 0 | 0 | 0 | 0 | 0 | 32153.3333 | 32153.3333 | 32153.3333 | 32153.3333 | 32153.3333 | 32153.3333 | 192920
Proc | TG-2324-PM09 |  | MCO - 250 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 850080 | 0 | 0 | 0 | 0 | 0 | 0 | 70840 | 70840 | 70840 | 70840 | 70840 | 70840 | 425040
Proc | TG-2324-PM10 |  | MCO - 500 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 488880 | 0 | 0 | 0 | 0 | 0 | 0 | 40740 | 40740 | 40740 | 40740 | 40740 | 40740 | 244440
Proc | TG-2324-PM11 |  | MCO - 600 ml - Sleeve - PAD Printing | Sivaraj | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 27160 | 0 | 0 | 0 | 0 | 0 | 0 | 2263.3333 | 2263.3333 | 2263.3333 | 2263.3333 | 2263.3333 | 2263.3333 | 13580
Proc | TG-2324-PM12 |  | MCO - Container : HDPE to PET with Sleeve | Sivaraj | Cancelled | 2023-04-01 | 2023-04-01 | 2023-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proc | TG-2324-PM13 | 5004396 | 18 ml - Indica - Colorant - Alternative Vendor | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-05-01 | 10085600 | 0 | 493476.7039 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 840466.6667 | 8898143.3705
Proc | TG-2324-PM14 | 5000718 | 18 mm - Indica - Middle layer - Alternative Vendor | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-05-01 | 13639290 | 0 | 639545.7252 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 1136607.5 | 12005620.7252
Proc | TG-2324-PM15 | 5007172/5004885 | Meera AD - Rs.2/- Shampoo - Alternative Vendor | Sivaraj | Done | 2023-04-01 | 2023-04-01 | 2023-04-01 | 3825000 | 1933801.3281 | 1098816.33 | 318750 | 318750 | 318750 | 318750 | 318750 | 318750 | 318750 | 318750 | 318750 | 318750 | 6220117.6581
Proc | TG-2324-PM16 | CFC | CFC - E Auction - UKM1 Plant (May'23 - Sep'23) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-05-01 | 22300000 | 73402.5091 | 1508669.6594 | 1858333.3333 | 1858333.3333 | 1858333.3333 | 1858333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 9015405.5019
Proc | TG-2324-PM17 | CFC | CFC - E Auction - Nikita Plant (Apr'23 - Sep'23) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-04-01 | 19400000 | 1505151.1695 | 1039158.4232 | 1616666.6667 | 1616666.6667 | 1616666.6667 | 1616666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 9010976.2594
Proc | TG-2324-PM18 |  | Forward Coverage - Laminate (June'23 - Sep'23) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-06-01 | 22000000 | 0 | 0 | 5500000 | 5500000 | 5500000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 22000000
Proc | TG-2324-PM19 | CFC | CFC - E Auction - Assam Plant (Jun'23 - Nov'23) | Sivaraj | Done | 2023-06-01 | 2023-06-01 | 2023-06-01 | 30048000 | 0 | 0 | 2504000 | 2504000 | 2504000 | 2504000 | 2504000 | 2504000 | 0 | 0 | 0 | 0 | 15024000
Non Proc | PG-2324-NP01 | 5001167/5001166 | Spinz BB Cream - Metalic to Non Metalic Cap | Nishanth | Pending | 2023-06-01 | 2023-06-01 | 2023-10-01 | 10482293.8 | 0 | 0 | 0 | 0 | 0 | 0 | 873524.4833 | 873524.4833 | 873524.4833 | 873524.4833 | 873524.4833 | 873524.4833 | 5241146.9
Non Proc | PG-2324-NP02 |  | Meera 340ML Container Weight Reduction | Nishanth | Pending | 2023-06-01 | 2023-06-01 | 2023-07-01 | 993600 | 0 | 0 | 0 | 82800 | 82800 | 82800 | 82800 | 82800 | 82800 | 82800 | 82800 | 82800 | 745200
Non Proc | PG-2324-NP03 | 5003983/5004397/ 5008130/5008290 | Developer Laminater Structure Change | Nishanth | Done | 2023-06-01 | 2023-06-01 | 2023-04-01 | 2028000 | 143165.3464 | 202351.404 | 169000 | 169000 | 169000 | 169000 | 169000 | 169000 | 169000 | 169000 | 169000 | 169000 | 2035516.7504
Non Proc | PG-2324-NP04 |  | Meera Shampoo Downguaging and Ink Removal | Nishanth | Pending | 2023-06-01 | 2023-06-01 | 2023-12-01 | 5040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 420000 | 420000 | 420000 | 1680000
Non Proc | PG-2324-NP05 |  | PCR bundling sleeves for PC | Nishanth | Done | 2023-06-01 | 2023-06-01 | 2023-04-01 | 1496000 | 63623.3372 | 216884.7717 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 124666.6667 | 1527174.7756
Non Proc | PL-2324-NP01 |  | Indica Easy | Sridhar | Pending | 2023-04-01 | 2023-04-01 | 2023-08-01 | 12800000 | 0 | 0 | 0 | 0 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 1066666.6667 | 8533333.3333
Non Proc | PL-2324-NP02 |  | Chik Re. 1 Fragrance | Sridhar | Pending | 2023-04-01 | 2023-04-01 | 2023-10-01 | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 8500000
Non Proc | PL-2324-NP03 | 4002873 | Chik 50p Fragrance - Fragrance Ophelia power - Alternative Material | Sridhar | Done | 2023-04-01 | 2023-04-01 | 2023-06-01 | 4000000 | 0 | 0 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 3333333.3333 | UKM1 from June and Nikita from July
[9 empty] | 130935690 | 3512355.0067 | 4779666.8417 | 13951824.1667 | 14265990.8333 | 14386990.8333 | 14386990.8333 | 5602974.1667 | 5602974.1667 | 3098974.1667 | 3098974.1667 | 3098974.1667 | 3098974.1667 | 88885663.515
New Projects
S. No | Material Code | Brand - Activity | Amount | Reason
1 | Outer CFC | Chik | Rs. 10/- | For Chik Rs. 1/- removing outer CFC and packing only bundle slevees - UKM1 machiery avaiable to be tried in Single State and in trails
2 | Lam and CFC | Meera | 5000000 | For Meera Rs. 2/- lam Structure to 10/10/25, CFC - Down Guaging
3 | Flow Wrap | Spinz BB Talc 25gms |  | Flow Wrap - Reduction in Hanger and CC Cost
4 | Actuator | Spinz Deo - All |  | Removal of Profile actuator and shaped cap
5 | Carton | Indica |  | Replace with hanger
6 | Carton | Spinz BB Cream - 15gms/29gms |  | To ideate removing the additional features in carton maintaining same size impression