## INFO
PROJECT INFO
PROJECT NAME | FINTECH APPLICATION
PROJECT START DATE | 2023-09-09
PROJECT END DATE | 2023-12-06
PERCENTAGE
COMPANY | HEPL
CLIENT NAME | SRIKANTH
PLATFORM | WEB & MOBILE APP
SPOC | VAIRAM
DEVELOPMENT HEAD | AISHWARYAA
DEVELOPMENT TL | GANAGAVATHY
DEVELOPERS | VIGNESHWARI
MOOVIKA
NISHA
TESTER | SURENDER
UI | KUMANAN
BUSINESS ANALYST | PUNITHA HARIHARAN

## SPRINT PLAN
S NO | SPRINT NAME | SPRINT TAT | MODULES | SUB MODULE | TASK | PRIORITY | TASK START DATE | TASK END DATE | BUFFER DATE | ASSIGNE | DEVELOPER STATUS | STATUS | COMPLETION PERCENTAGE | REMARKS
1 | SPRINT 1 | ONE WEEK | UI |  | To do complete UI prototype | P1 | 2023-09-09 | 2023-09-19 |  | KUMANAN |  | COMPLETED | 100
2 | SPRINT 2 | THREE WEEKS | USER MANAGEMENT | ROLES | Front end design based on the UI prototype and back end process with complete fucntionality | P1 | 2023-09-20 | 2023-10-13 |  | VIGNESHWARI , MOOVIKA, NISHA | INPROGRESS | INPROGRESS | 75
|  |  |  | PERMISSION | [6 empty] | INPROGRESS | INPROGRESS | 75
|  |  |  | USER CREATION | [6 empty] | INPROGRESS | INPROGRESS | 75
|  |  |  | LOGIN | [6 empty] | INPROGRESS | INPROGRESS | 75
|  |  | MASTER MANAGEMENT | GENERAL MASTERS | [6 empty] | INPROGRESS | INPROGRESS | 75
3 | SPRINT 3 | THREE WEEKS | PARTNER MANAGEMENT | PARTNER ONBOARD | Front end & back end development for the process of from partner addition to Partner product mapping | P1 | 2023-10-16 | 2023-11-03 |  | VIGNESHWARI , MOOVIKA, NISHA
PARTNER LEAD
PARTNER VERIFICATION
PARTNER PRODUCT MAPPING
4 | SPRINT 4 | THREE WEEKS | LEAD MANAGEMENT | LEAD GENERATION | Front end and back end developement for the lead management which includes the lead generation, lead modification by the ops exe and data preview as per the hierarchy level | P1 | 2023-11-06 | 2023-11-25 |  | VIGNESHWARI , MOOVIKA, NISHA
LEAD MODIFICATION
DSR
|  |  | PROJECT TESTING |  | Testing on entire portal by testing team before UAT sharing |  | 2023-11-27 | 2023-12-06 |  | SURRENDAR